## Sheet1
Task ID | Task Name | SubtasK ID | Subtask Name | Estimated Hours | Assigned To | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Hours Spent | Notes
1 | Project Initiation
|  | 1.1 | Project Kickoff Meeting | 8 | Team |  |  |  |  | Done
|  | 1.2 | Identify Stakeholders | 5 | Sitti Monera F. Martin |  |  |  |  | Done
|  | 1.3 | Define Project Scope | 10 | Honey Jane P. pangasate |  |  |  |  | Done
|  | 1.4 | Create Project Charter | 3 | Team |  |  |  |  | Done
|  | 1.5 | Finalize Project Plan | 10 | Sitti Monera F. Martin |  |  |  |  | Done
2 | Requirements Analysis
|  | 2.1 | Gather Functional Requirements | 16 | Team |  |  |  |  | Done
|  | 2.2 | Document Requirements | 10 | Honey Jane P. Pangasate |  |  |  |  | Done
|  | 2.3 | Requirements Review | 2 | Kyle Alonzo |  |  |  |  | Done
3 | Design Phase
|  | 3.1 | Conceptual Design | 20 | Sitti Monera F. Martin |  |  |  |  | Done
|  | 3.2 | Design Review | 4 | Kyle Alonzo |  |  |  |  | Done
|  | 3.3 | Create Detailed Design | 48 | Team |  |  |  |  | Done
|  | 3.4 | Finalize Design | 8 | Honey Jane Pangaasate |  |  |  |  | Done
4 | Implementation
|  | 4.1 | Phase 1 Implementation | 80 | Team |  |  |  |  | Done
|  | 4.2 | Phase 2 Implementation | 80 | Team |  |  |  |  | Done
|  | 4.3 | Implementation Review | 10 | Team |  |  |  |  | Done
5 | Testing
|  | 5.1 | Unit Testing | 16 | Sitti Monera F. Martin |  |  |  |  | Done
|  | 5.2 | Perform Test Case | 24 | Honey P. Pangasate |  |  |  |  | Done
|  | 5.3 | Error Correction | 20 | Kyle Alonzo |  |  |  |  | Done
6 | Deployment
|  | 6.1 | Create Deployment Plan | 8 | Team |  |  |  |  | Done
|  | 6.2 | Deployment | 20 | Team |  |  |  |  | Done
|  | 6.3 | Deployment Assessment | 10 | Team |  |  |  |  | Done
7 | Project Closure
|  | 7.1 | Capture Project Insights | 101 | Honey Jane P. Pangasate |  |  |  |  | Done
|  | 7.2 | Final Project Documentation | 16 | Team |  |  |  |  | Done